## Week1
Capstone Project 1
Project Name 4 | Employee Staffing Optimization | Project Duration 4 | TBA
Facilitator 4 | Dennis Buttera, Yash Kanani
Team Members 4 | Young Bong Ko | Project Start 4 | 02-12-2024
Gayathri Gnanam
| Jaishaanth Suresh | Project End 4 | TBA
Mahesha Sree Sivasubramanian
Shithi Saha
Project Background 4 | By analyzing historical data from 2019 and 2022 to 2024, the goal is to perform EDA and develop Machine Learning models to calculate the optimum number of employees required for the year 2024.
|  | Total Tasks 4 | 9
|  | In progress 4 | 4
|  | Completed 4 | 0
Task | Assigned to | Progress | Status
Data Preparation | Jaishaanth/ Shithi | 50% | In Progress
Exploratory Data Analysis | Shithi / Youngbong | 50% | In Progress
Feature Engineering | Jaishaanth/ Youngbong | 30% | In Progress
ML model 1 |  |  | Not Started
ML model 2 |  |  | Not Started
ML model 3 |  |  | Not Started
Optimal Model Selection |  |  | Not Started
Dashboard Visualization | Gayathri / Mahesha | 10% | In Progress
Report |  |  | Not Started
Questions for the meeting
When can we get the other data?
Check the null value sections in the data set ( ex > postal code)

## Week3
Capstone Project 1
Project Name 4 | Employee Staffing Optimization | Project Duration 4 | TBA
Facilitator 4 | Dennis Buttera, Yash Kanani
Team Members 4 | Young Bong Ko | Project Start 4 | 02-12-2024
Gayathri Gnanam
| Jaishaanth Suresh | Project End 4 | TBA
Mahesha Sree Sivasubramanian
Shithi Saha
Project Background 4 | By analyzing historical data from 2019 and 2022 to 2024, the goal is to perform EDA and develop Machine Learning models to calculate the optimum number of employees required for the year 2024.
|  | Total Tasks 4 | #VALUE!
|  | In progress 4 | 4
|  | Completed 4 | 0
Task | Assigned to | Progress | Status | Note
Data Preparation | Jaishaanth/ Shithi | 50% | In Progress
Exploratory Data Analysis | Shithi / Youngbong | 50% | In Progress
Feature Engineering | Jaishaanth/ Youngbong | 30% | In Progress
ML model 1 |  | 5% | In Progress
ML model 2 |  | 5% | In Progress | Decision Tree
ML model 3 | Jaishaanth | 30% | In Progress | Random forest
ML model 4 | Mahesha Sree | 70% | In Progress | Ensemble
ML model 5 |  | 5% | In Progress | Logistic Regression
ML model 6 |  | 5% | In Progress | Support Vector Machines
ML model 7 |  | 5% | In Progress | Nural Network
Optimal Model Selection |  |  | Not Started
Dashboard Visualization | Gayathri / Mahesha/Jaishaanth/Youngbong/Shithi | 10% | In Progress
Report |  |  | Not Started
Questions for the meeting |  |  |  | Note
When Volume loaded, how long does it take to be delivered.
How much is expected coverage for one person work hour.
Total Actual Work time | 10272275
Total Work Load | 35557134
PPH(Parcel per hour) | 3.4615
1.7

## Week4
Capstone Project 1
Project Name 4 | Employee Staffing Optimization | Project Duration 4 | TBA
Facilitator 4 | Dennis Buttera, Yash Kanani |  |  |  | 39
Team Members 4 | Young Bong Ko | Project Start 4 | 02-12-2024
Gayathri Gnanam
| Jaishaanth Suresh | Project End 4 | TBA
Mahesha Sree Sivasubramanian
Shithi Saha
Project Background 4 | By analyzing historical data from 2019 and 2022 to 2024, the goal is to perform EDA and develop Machine Learning models to calculate the optimum number of employees required for the year 2024.
|  | Total Tasks 4 | 39
|  | In progress 4 | 22
|  | Completed 4 | 0
Task | Assigned to | Progress | Status | Note
Feature Engineering |  | Jaishaanth/ Youngbong | 50% | In Progress | 1
Feature Engineering | Add ML file and set some scripts for invesigation | Youngbong | 30% | In Progress | 1
ML for Workload | Linear Regression | Youngbong | 10% | In Progress | 1
| Decision Tree | Youngbong | 10% | In Progress | 1
| Random forest | Youngbong | 10% | In Progress | 1
| Ensemble | Youngbong | 10% | In Progress | 1
| Logistic Regression | Youngbong | 10% | In Progress | 1
| Support Vector Machines | Youngbong | 10% | In Progress | 1
| Nural Network | Youngbong | 10% | In Progress | 1
Optimal Model Selection |  |  |  | Not Started | 1
ML for Planned Absence | Linear Regression |  |  | Not Started | 1
| Decision Tree |  |  | Not Started | 1
| Random forest |  |  | Not Started | 1
| Ensemble |  |  | Not Started | 1
| Logistic Regression |  |  | Not Started | 1
| Support Vector Machines |  |  | Not Started | 1
| Nural Network |  |  | Not Started | 1
Optimal Model Selection |  |  |  | Not Started | 1
ML for Unplanned Absence | Linear Regression |  |  | Not Started | 1
| Decision Tree |  |  | Not Started | 1
| Random forest |  |  | Not Started | 1
| Ensemble |  |  | Not Started | 1
| Logistic Regression |  |  | Not Started | 1
| Support Vector Machines |  |  | Not Started | 1
| Nural Network |  |  | Not Started | 1
Optimal Model Selection |  |  |  | Not Started | 1
Data Preparation | Jaishaanth/ Shithi | 50% | In Progress |  | 1
Exploratory Data Analysis | Shithi / Youngbong | 50% | In Progress |  | 1
Feature Engineering | Jaishaanth/ Youngbong | 30% | In Progress |  | 1
ML model 1 |  | 5% | In Progress |  | 1
ML model 2 |  | 5% | In Progress | Decision Tree | 1
ML model 3 | Jaishaanth | 30% | In Progress | Random forest | 1
ML model 4 | Mahesha Sree | 60% | In Progress | Ensemble | 1
ML model 5 |  | 5% | In Progress | Logistic Regression | 1
ML model 6 |  | 5% | In Progress | Support Vector Machines | 1
ML model 7 |  | 5% | In Progress | Nural Network | 1
Optimal Model Selection |  |  | Not Started |  | 1
Dashboard Visualization | Gayathri / Mahesha/Jaishaanth/Youngbong/Shithi | 10% | In Progress |  | 1
Report |  |  | Not Started |  | 1
Questions for the meeting |  |  |  | Note
Weather data doesn't affect to the workload |  |  |  | The current data doesn't
Created Short scripts for ML and ran them through data, without any adjustment. And the result is not meaningful at all for now.
Condition of the Planned Absence trand is another key point
Condition of the Unplanned Absence Trand is another key point

## Task Detail
Task |  | Assigned to | Progress | Status | Note
Data Preparation |  | Jaishaanth/ Shithi | 50% | In Progress
| merge by day for Worker_attendance | Youngbong | 100%
| merge by day for Item_CostCenter | Youngbong | 100%
| Merge by day Weather | Youngbong | 100%
| Merge altogether for ML | Youngbong | 100%
| Created additional columns to the main data set | Youngbong | 80% |  | Actual Work Hours(Sum) EWH by Load Daily remain Rough esteam of merged workload
Exploratory Data Analysis
Shipping Volume
Weather Condition
| Customer Behavior |  |  |  | Attendance
| Economic Trend |  |  |  | ex> Temu launches their market
Advanced system
Global/Local Events
Feature Engineering |  | Jaishaanth/ Youngbong | 50% | In Progress
Feature Engineering | Add ML file and set some scripts for investigation | Youngbong | 30% | In Progress
ML for Workload | Linear Regression | Youngbong | 10% | In Progress
| Decision Tree | Youngbong | 10% | In Progress
| Random forest | Jaishaanth/Youngbong | 30% | In Progress
| Ensemble | Youngbong | 10% | In Progress
| Logistic Regression | Youngbong | 10% | In Progress
| Support Vector Machines | Youngbong | 10% | In Progress
Neural Network
| Time Series | Mahesha Sree | 70% | In Progress
Optimal Model Selection |  |  |  | Not Started
ML for Planned Absence | Linear Regression | Rayathri |  | Not Started
| Decision Tree | Rayathri |  | Not Started
| Random forest | Jaishaanth |  | Not Started
| Ensemble | Jaishaanth |  | Not Started
| Logistic Regression | Youngbong |  | Not Started
| Support Vector Machines | Youngbong |  | Not Started
| Neural Network | Youngbong |  | Not Started
Optimal Model Selection |  |  |  | Not Started
ML for Unplanned Absence | Linear Regression | Rayathri |  | Not Started
| Decision Tree | Rayathri |  | Not Started
| Random forest | Jaishaanth |  | Not Started
| Ensemble | Jaishaanth |  | Not Started
| Logistic Regression | Youngbong |  | Not Started
| Support Vector Machines | Youngbong |  | Not Started
| Neural Network | Youngbong |  | Not Started
Optimal Model Selection |  |  |  | Not Started
Dashboard Visualization |  | Gayathri / Mahesha | 10% | In Progress
| Delivery load by Season | Shithi | 20% | In Progress
| Overall Seasonality and trends | Mahesha Sree | 70% | In Progress
| Employee vacation by Season | Shithi | 20% | In Progress
Severe weather conditions by Season
Employee vacation by Weekday
Delivery load by Weekday
Employee vacation by Weekday
Workload VS upcoming Anniversary or event
Report |  |  |  | Not Started
Created
Created Short scripts for ML and ran them through data, without any adjustment. And the result is not meaningful at all for now.
Condition of the Planned Absence trand is another key point
Condition of the Unplanned Absence Trand is another key point
| Workload sum / actual workhour sum = PPh( parcle per hour) 35557134/6341983.18= 5.606627138546414 ~ 5.6 |  |  |  | There was period of no parcle during the covid, so I remove that period.