## Week1
Capstone Project 1
Project Name 4 | Employee Staffing Optimization | Project Duration 4 | TBA
Facilitator 4 | Dennis Buttera, Yash Kanani
Team Members 4 | Young Bong Ko | Project Start 4 | 02-12-2024
Gayathri Gnanam
| Jaishaanth Suresh | Project End 4 | TBA
Mahesha Sree Sivasubramanian
Shithi Saha
Project Background 4 | By analyzing historical data from 2019 and 2022 to 2024, the goal is to perform EDA and develop Machine Learning models to calculate the optimum number of employees required for the year 2024.
|  | Total Tasks 4 | 9
|  | In progress 4 | 4
|  | Completed 4 | 0
Task | Assigned to | Progress | Status
Data Preparation | Jaishaanth/ Shithi | 50% | In Progress
Exploratory Data Analysis | Shithi / Youngbong | 50% | In Progress
Feature Engineering | Jaishaanth/ Youngbong | 30% | In Progress
ML model 1 |  |  | Not Started
ML model 2 |  |  | Not Started
ML model 3 |  |  | Not Started
Optimal Model Selection |  |  | Not Started
Dashboard Visualization | Gayathri / Mahesha | 10% | In Progress
Report |  |  | Not Started
Questions for the meeting
When can we get the other data?
Check the null value sections in the data set ( ex > postal code)

## Week3
Capstone Project 1
Project Name 4 | Employee Staffing Optimization | Project Duration 4 | TBA
Facilitator 4 | Dennis Buttera, Yash Kanani
Team Members 4 | Young Bong Ko | Project Start 4 | 02-12-2024
Gayathri Gnanam
| Jaishaanth Suresh | Project End 4 | TBA
Mahesha Sree Sivasubramanian
Shithi Saha
Project Background 4 | By analyzing historical data from 2019 and 2022 to 2024, the goal is to perform EDA and develop Machine Learning models to calculate the optimum number of employees required for the year 2024.
|  | Total Tasks 4 | 9
|  | In progress 4 | 4
|  | Completed 4 | 0
Task | Assigned to | Progress | Status | Note
Data Preparation | Jaishaanth/ Shithi | 50% | In Progress
Exploratory Data Analysis | Shithi / Youngbong | 50% | In Progress
Feature Engineering | Jaishaanth/ Youngbong | 30% | In Progress
ML model 1 |  |  | Not Started
ML model 2 |  |  | Not Started
ML model 3 |  |  | Not Started
ML model 4 |  |  | Not Started
ML model 5 |  |  | Not Started
ML model 6 |  |  | Not Started
ML model 7 |  |  | Not Started
ML model 8 |  |  | Not Started
Optimal Model Selection |  |  | Not Started
Dashboard Visualization | Gayathri / Mahesha | 10% | In Progress
Report |  |  | Not Started
Questions for the meeting |  |  |  | Note
When can we get the other data?
Check the null value sections in the data set ( ex > postal code)

## Task Detail
Task | Assigned to | Progress | Status | Note
Data Preparation | Jaishaanth/ Shithi | 50% | In Progress
Exploratory Data Analysis | Shithi / Youngbong | 50% | In Progress
Feature Engineering | Jaishaanth/ Youngbong | 30% | In Progress
ML model 1 |  |  | Not Started
ML model 2 |  |  | Not Started
ML model 3 |  |  | Not Started
ML model 4 |  |  | Not Started
ML model 5 |  |  | Not Started
ML model 6 |  |  | Not Started
ML model 7 |  |  | Not Started
ML model 8 |  |  | Not Started
Optimal Model Selection |  |  | Not Started
Dashboard Visualization | Gayathri / Mahesha | 10% | In Progress
Report |  |  | Not Started